## Sheet1
Controlling Project Costs and Risks
Summer 2008
Team #3 (Raisa, Omar, Roberto, David, Mark, Suzanne)
Week #2 and #3 Team Exercise
WBS for Charity Project
Charity Event WBS
1. Managing the projects
1.1. Designate a project manager for the overall project
1.1.1. Work with web team to put information on company intranet
1.2. Designate leaders for each of the four campaigns
1.3. Create a scope statement
1.4. Create a work breakdown structure
1.5. Create a cost analysis for each of the four campaigns
1.5.1. Capital campaign
1.5.2. Soccer tournament
1.5.3. Catalog fundraiser
1.5.4. Phone bank
1.6. Execute the plan
1.7. Monitor activities
1.8. Write project wrap up report
2. Capital campaign
2.1. Research prospective donors
2.2. Contact donors and submit business donation case
2.3. Market campaign to large businesses and small firms
2.3.1. Meet with directors and owners to discuss fundraising initiative
2.3.2. Discuss firm and small business matching contribution from employee donations
2.3.3. Create advertising space on MedImpact soccer game for advertisement space
3. Soccer tournament
3.1. Form tournament planning committee (volunteers)
3.1.1. Send email asking for volunteers
3.1.2. Host Q&A meeting
3.1.3. Host weekly meeting
3.2. Look for sponsors
3.2.1. Call possible sponsors
3.2.2. Put together presentation
3.2.3. Meet with candidate sponsors
3.3. Establish location
3.3.1. Research locations
3.3.2. Pick location
3.4. Recruit staff
3.4.1. Recruit referees (volunteers)
3.4.2. Recruit support staff (sign up table, clean up, etc.)
3.5. Event literature
3.5.1. Put together tournament rules
3.5.2. Tournament flyer
3.5.3. Tournament web site
3.6. Collect and cash entries
3.7. Tournament t-shits
3.7.1. Design art
3.7.2. Add sponsor logos
3.7.3. Print t-shirts
3.8. Tournament equipment
3.8.1. Purchase soccer balls
3.8.2. Purchase goals
3.9. Tournament draw
3.9.1. Put together tournament draw
3.9.2. Put together match schedule
3.9.3. Post tournament schedule and times on web site
3.9.4. Tournament day
3.9.5. Put together information and registration tables
3.9.6. Team sign-up
3.9.7. Tournament play
3.9.8. Winner ceremony
3.9.9. Clean up
4. Catalog fundraiser
4.1. Contact Charles Chips for order forms and catalogs
4.2. Distribute order forms, catalogs, and internal memo about the 6-month catalog campaign
4.2.1. Periodically collect order forms and money
4.2.2. Submit orders to Charles Chips and remit 20% to fundraiser
4.3. Receive and accurately distribute orders
5. Phone bank
5.1. Research how to organize and implement a phone bank
5.2. Find a suitable location and equipment within the company to hold phone bank campaign
5.3. Work with web team to put information on company intranet
5.4. Recruit callers
5.5. Hold a training session for callers
5.5.1. With callers, develop a script to use for phone calls
5.5.2. Discuss phone etiquette and tips
5.6. Hold phone bank campaign
1.0
(from page 1)
Managing the projects
1.1
Designate a project manager for the overall project
1.2. Designate leaders for each of the four campaigns
1.3. Write a preliminary scope statement
1.4. Write a work breakdown structure
1.5. Create a cost analysis for each of the four campaigns
1.6. Catalog fundraiser Execute the plan
1.7. Monitor activities
1.8. Write project wrap up report
1.1.1
Work with web team to put information on compan
1.5.1. Capital campaign
1.5.2. Soccer tournament
1.5.3. Catalog fundraiser
1.5.3. Catalog fundraiser
2.0
(from page 1)
Capital campaign
2.1
Research prospective donors
2.2.
Contact donors and submit business donation case
2.3.
Market campaign to large businesses and small firms
2.3.1.
Meet with directors and owners to discuss fundraising
2.3.2.
Discuss firm and small business matching contribution
2.3.3.
Create advertising space on MedImpact soccer game
3.0
(from page 1)
Soccer tournament
3.1. Form tournament planning committee (volunteers)
3.2. Look for sponsors
3.3. Establish location
3.4. Recruit staff
3.5. Event literature
3.6. Collect and cash entries
3.7. Tournament t-shits
3.8. Tournament equipment
3.9. Tournament draw
3.1.1. Send email asking for volunteers
3.1.2. Host Q&A meeting
3.1.3. Host weekly meeting
3.2.1. Call possible sponsors
3.2.2. Put together presentation
3.2.3. Meet with candidate sponsors
3.3.1. Research locations
3.3.2. Pick location
3.4.1. Recruit referees (volunteers)
3.4.2. Recruit support staff (sign up table, clean up, etc.)
3.5.1. Put together tournament rules
3.5.2. Tournament flyer
3.5.3. Tournament web site
3.7.1. Design art
3.7.2. Add sponsor logos
3.7.3. Print t-shirts
3.8.1. Purchase soccer balls
3.8.2. Purchase goals
3.9.1. Put together tournament draw
3.9.2. Put together match schedule
3.9.3. Post tournament schedule and times on web site
3.9.4. Tournament day
3.9.5. Put together information and registration tables
3.9.6. Team sign-up
3.9.7. Tournament play
3.9.8. Winner ceremony
3.9.9. Clean up
4.0
(from page 1)
Catalog fundraiser
4.1.
Contact Charles Chips for order forms and catalogs
4.2.
Distribute order forms, catalogs, and internal memo about
4.3.
Receive and accurately distribute orders
4.2.1.
Periodically collect order forms and money
4.2.2.
Submit orders to Charles Chips and remit 20% to fundraiser
5.0
(from page 1)
Phone bank
5.1. Research how to organize and implement a phone bank
5.2.
Find a suitable location and equipment within the company
5.3.
Work with web team to put information on company intranet
5.4.
Recruit callers
5.5.
Hold a training session for callers
5.6.
Hold phone bank campaign
5.5.1.
With callers, develop a script to use for phone calls
5.5.2.
Discuss phone etiquette and tips
Charity Event
1.0
Managing the projects
(see page 2)
2.0
Capital campaign
(see page 3)
3.0
Soccer tournament
(see page 4)
4.0
Catalog fundraiser
(see page 6)
5.0
Phone bank
(see page 7)