July 20, 2008

Preliminary Scope Statement

Product and Project Objectives

Our Company (“Projecto La Torre Incorporated”) has been contracted by the ministry of infrastructure of the government of Venezuela (short for “Republica Bolivariana de Venezuela”) to construct 5 miles of railway embankment at a remote location in the state of Guarico (8 hours drive from the capital). This project is part of the initiative by the government of Venezuela to expand the national railway system as stated in Venezuela’s constitution of 1999.

The project involves: Financing, recruitment, construction of temporary infrastructure (dorms, cafeteria, offices, storage, etc), purchase of machinery, purchase materials and the construction of train tracks bed.

Product Requirements and Characteristics

5 miles of railway embankment should be constructed

9 months should be duration of the product creation

$4,000,000 should be spent

Product acceptance criteria

5 miles of railway embankment installed up to specifications (please refer to “Project Requirements and Deliverables”)

Project is finished before the rainy season

Product boundaries

Only 5 miles of railway embankment will be installed.

Company is not responsible in laying down the actual metal train tracks. Installation will be done by another company scheduled to work right behind us.

Project Requirements and Deliverables

5 miles of the railway embankment, the embankment must measure approximately 47 meters in length at the base and about 17 meters in length at the top.  The Embankment (including the base) has to be a least 5 meter tall, since the rainwater, at its highest level, should never reach the tracks. Please refer to the picture bellow:

Tracks

47 m

5 m

17 m

EMBANKMENT

0.5 m

Base/Foundation

Project Constraints

Time: 9 months

Money: $4,000,000

Quality: 5 Miles of railway embankment should be ready to be used for installing metal train tracks.

Project Assumptions

Project will be completed before the rainy season begins. Work cannot be done during the rainy season.

Temporary infrastructure and heavy equipment will be reuse to build additional railway embankment miles outside the scope of this project. It is expected that The State Railways Autonomous Institute (IAFE) will grant a new contract after they original contract has been completed up to theirs satisfaction.

We do not have to worry about unions.

Bribery is part of the culture in this part of the world..

Unknown irregular groups are known to be present in the area. Security, in the form of armed guards, is required to avoid theft of equipment.

Initial Project Organization

Government of Venezuela

!

Project  Management Team

!

Projecto La Torre Incorporated Company

Initial Defined Risks

Rainy season may start earlier

Equipment delivery may be delayed

Instability of local currency.

Political unrest.

Schedule milestones

Acquire financing

Successful recruitment

Construction of temporary infrastructure

Purchase of heavy equipment

Purchase of materials

Construction of railway embankment.

Initial WBS

- Construction of national railway.

  - Acquire Financing:

    - Executive summary.

    - Banks negotiation.

  - Recruitment.

    - Advertisements in local newspapers.

    - Interviews holding.

    - Staff selection.

  - Construction of temporary infrastructure.

    - Construction of sleeping quarters (inc. bathrooms).

    - Construction of cafeteria.

    - Construction of offices.

    - Construction of storage facilities.

    - Electric system.

      - Purchase of generator.

      - Installation.

  - Purchase of heavy equipment (for example: excavator, dump trucks, etc.)

  - Purchase of materials.

  - Construction of railway embankment.

    - Surveyors mapping of the railroad route.

    - Railroad route preparation.

    - Foundation installation.

    - Embankment installation.

Order of magnitude cost estimate

$4,000,000

Project Configuration management requirements

CM should ensure accurate and up-to-date documentation and distribution of all relevant product components and project information.

The configuration management plan should be produced as part of the project initiation document.

A configuration item description record should be used to record the information needed to identify and track each configuration item through its development life cycle.

Approval Requirements

The State Railways Autonomous Institute (IAFE) approval of he project deliverables required.